## Sheet1
# | Issue | Severity | Type | Tables / Files | Status
1 | Duplicate bill_prefix on 2 companies — blocks migration 001 | 🔴 High | Data + DB | header_master | ❌ Pending
2 | Migration 001 — unique index on bill_prefix not yet applied | 🔴 High | DB | header_master | ❌ Pending (blocked by #1)
3 | Delete DRAFT bill failing — root cause not confirmed yet | 🔴 High | App + DB | bills, bill_merges, bill_payments | ❌ Needs investigation
4 | Delete company blocked — code checks header_id bills but misses override_header_id FK | 🟠 Medium | App + DB | bills, header_master | ❌ Pending
5 | Broken update_bill_payment_status_on_delete trigger on prod — missing last_payment_date update | 🟠 Medium | DB | bill_payments, bills | ❌ Migration 003 not run on prod
6 | Migration 004 — zero-value finalize guard not yet applied | 🟠 Medium | DB | bills | ❌ Pending
7 | Migration 005 — duplicate trigger on bill_payments + dead bill_number_sequence table | 🟠 Medium | DB | bill_payments, bill_number_sequence | ❌ Pending
8 | gst_rates_master has orphan rate_name column in prod not in schema | 🟡 Low | DB | gst_rates_master | ❌ Pending
9 | Finalized bills can be deleted by anyone — no status guard in deleteBill | 🟡 Low | App | bills | ❌ Pending
10 | DROP old write-off columns from bills after data verified | 🟡 Low | DB | bills | ❌ Hold until confirmed
11 | WRITE_OFF_BILL activity log has entity_type = "bill" (lowercase) — inconsistent | 🟡 Low | App | activity_log | ❌ Pending